## STAR
[PROJECT] | FTE - Staff | FTE - PD | Physics program summary (highlights, deliverables, etc...) | Notes
Current FTE | 2.6 | 3.3 |  | XD: Currently both Guannan and Yue-Hang have left. So PD should be down by 2 (or 1.8). For staff, Jim is retiring this month.
0-2 years: baseline | 1.5 | 2 | BES-II high precision measurement (collider and FXT): collective flows, net-proton moments, strangeness, hypernuclei, di-electrons | FTE Staff: 0.5 (XD) + 0.5 (NX) + 0.3 (GO) + 0.2 (PJ)
3-5 years: baseline | 0.3 | 0.25 | completion of BES-II analyses + publications
6-10 years: baseline | 0 | 0 | remaining analyses, may be shared with sPHENIX personpower depending on the status |  | x
0-2 years: expanded | 1.5 | 2 |  | [Useful to include notes on dependences, e.g. 3-5 year plan is (is not) contingent on expanded effort in years 0-2]
3-5 years: expanded | 0.6 | 0.5
6-10 years: expanded | 0.3 | 0.3
0-2 years: minimal | 0 | 0 |  | [Useful to include notes on dependences, e.g. cuts in the 0-2 year window ensure that the 3-5 year effort will be at "minimal" level]
3-5 years: minimal | 0 | 0
6-10 years: minimal | 0 | 0

## sPHENIX
[PROJECT] | FTE - Staff | FTE - PD | Physics program summary (highlights, deliverables, etc...) | Notes
Current FTE | 1.4 | 1.3 |  | MP: does FTE - PD includes .5FTE of Nacer? - it should presently. XD: current staff includes Yuan, while Yuan is not included in the planning in the following rows
0-2 years: baseline | 0.8 | 1.5 | MVTX construction, comissioning, calibration, operation (2023-2026); start of heavy flavor physics analyses: open bottom production/collectivity, HF baryons, D/Dbar v1 for initial B-field | FTE Staff: 0.3 (XD) + 0.2 (NX) + 0.3 (GO), if Yuan is counted, will be 1.5 FTE for Staff
3-5 years: baseline | 1.5 | 2.5 | Continue on heavy flavor physics analyses (to approximatelly 2028 ?), open bottom production/collectivity, HF baryons, D/Dbar v1 for initial B-field
6-10 years: baseline | 0.6 | 0.75 | finalizing the physics analyses + publications | XD: The walkdown will depend on the sPHENIX data production/analysis process. There is a concern at current stage on the shortage of computing resource at BNL.
0-2 years: expanded | 0.8 | 1.5 |  | [Useful to include notes on dependences, e.g. 3-5 year plan is (is not) contingent on expanded effort in years 0-2]
3-5 years: expanded | 1.5 | 2.5
6-10 years: expanded | 1.2 | 1.5
0-2 years: minimal | 0 | 0 |  | [Useful to include notes on dependences, e.g. cuts in the 0-2 year window ensure that the 3-5 year effort will be at "minimal" level]
3-5 years: minimal | 0 | 0
6-10 years: minimal | 0 | 0

## CBM
[PROJECT] | FTE - Staff | FTE - PD | Physics program summary (highlights, deliverables, etc...) | Notes | FTE - Staff (notes) | FTE - PD (notes)
Current FTE | 0.3 | 0
0-2 years: baseline | 0.3 | 0 | 2023-203? MAPS silicon detector upgrade, physics interest: proton high moments, hypernuclei (Y-Y), dileptons. Search for QCD CP and complete the beam energy scan program. Structure of QCD phase diagram at high baryon region. | Seek for DOE support US-CBM program
3-5 years: baseline | 0.6 | 0.5 |  | [need to define level of DOE support needed to support at this level]
6-10 years: baseline | 0.9 | 1
0-2 years: expanded | 1.75 | 1 | CBM is funded by DOE as part its HI program at high baryon density region. Work on the upgrade of the pixel-tracker at CBM. Physics: (i) QCD CP; (ii) Hyper nuclei program -> connect with Astro-nuclear physcics. | 1FTE and 1 PD will be needed to work on the pixel-tracker at CBM. | 1.75=0.75 (NX)+1 (XX) | 1
3-5 years: expanded | 2.5 | 2 | Prepare CBM for data taking. Near the end of the period, physics analysis starts. | More effots needed for the installation and calibrtion of the tracker + physics analysis at the end of the period | 2.5=1 (NX) + 1.5 (XX) | 2
6-10 years: expanded | 1.5 | 2 | (1) Physics analysis starts, search for QCD CP, hypernuclei production at high baryon dnesity and 1st order phase boundary; (2) Deterctor upgrade. | Data analysis and calibration. | 1.5=1 (NX) + 0.5 (XX) | 2
0-2 years: minimal | 0 | 0 | ["Minimal" is the level below which the program may not be sufficiently interesting and/or viable to pursue. Describe losses from the baseline program if workforce set to a "minimal" level (or else explain what key parts remain)] | [Useful to include notes on dependences, e.g. cuts in the 0-2 year window ensure that the 3-5 year effort will be at "minimal" level]
3-5 years: minimal | 0 | 0
6-10 years: minimal | 0 | 0

## ALICE
[PROJECT] | FTE - Staff | FTE - PD | Physics program summary (highlights, deliverables, etc...) | Notes
Current FTE | 2.7 | 1.7 | There is an additional 0.7 FTE Staff (ALICE computing), 1.0 PD support from UCB |  | Mateusz estimates 1.95+2.3 - need to make it add up
0-2 years: baseline | 3.5 | 4.5 | finalization of ongoing analyses; first analyses of new PbPb data - jet quenching: inclusive jet properties; semi-inclusive correlations; HF jet yields; search for jet quenching in pp; high-stat vector mesons in UPCs; continued effort developing and applying ML techniques - new methodology / unconventional measurements; TDR for FoCal and ITS3; ALICE 3 R&D | Staff: 3-4.5 depending on how to count Irakli/Jeff, Nikki, Leo; Postocs: 3-5 depending on how to count Yue Shi, Alberto Collu; Named staff: Barbara, Irakli/Jeff (computing), Nikki/Leo, Mateusz, Peter, Spencer; EIC-ALICE cross-talk to be fully understood; consideration: conversion(t) of staff->NxPD | from SC Fellow funds: 50% of Rey, Wenqing, 100% of Yue Shi in FY22; timescale for those funds to run out ~2 years.
3-5 years: baseline | 3.5 | 4 | LHC Run 3 data: details of jet quenching - QGP transport: high stat jet substructure; HF transport coefficient - HF in jets; more exotic UPCs; stringent limits on jet quenching in small systems; contributions to construction of FoCal and ITS3; contribution to ALICE 3 R&D | - contribution to FoCal construction on the level of 1 staff 2 PDs; ITS3 is a cross-collab with EIC; partial synergies to be explored/exploitet; assuming ALICE-USA computing @ Berkeley | FTE count includes 0.5 each for Barbara, Nikki, Spencer; all synergistic with EIC. I suggest not counting Alberto or Leo. MP: neither Alberto nor Leo were counted.
6-10 years: baseline | 3.5 | 4 | LHC Run 3+4 data:details of jet quenching - QGP transport: high stat jet substructure; HF transport coefficient - HF in jets (including dead-cone with b-jets); quark-jet quenching with central rapidity photons;exotic UPCs; small-x saturation - photons with FoCal; jet-jet forward-central correlations; TDR/construction of ALICE 3 - slight increase | - common R&D and potentially construction elements for ALICE 3 and EIC detector - cross-correl. TBD
0-2 years: expanded | 4 | 7 | instrumentation: larger leadership in FoCal and ITS3; physics: baseline contains main physics topics - more measurements / papers in reach with additional FTE - detailed list TBD; one clear expansion is more differential correlations with respect to (n-th) order event plane - event shape engeneering - etc; larger effort in machine learning techniques | 3-5 year plan is contingent on expanded effort in years 0-2 - larger contribution to R&D translated to more resp. in construction;
3-5 years: expanded | 4.5 | 6 | same as above + greater in instrumentationl; follow up on expanded involvement/lead/scope in FoCal/ITS3 construction but also ALICE 3 R&D | - common R&D and potentially construction elements for ALICE 3 and EIC detector - cross-correl. TBD
6-10 years: expanded | 4 | 6 | same as above + stronger involvement/lead/scope in ALICE 3 R&D and construction; physics: lead small-x and forward-central correlations [jets/HF] with FoCal; lead HF-jet correlations and substructure measurements in central rapidity; larger effort in machine learning techniques | - common R&D and potentially construction elements for ALICE 3 and EIC detector - cross-correl. TBD
0-2 years: minimal | 3 | 3 | - finalize currently ongoing analyses - no planned analyses; withdraw from FoCal and/or ITS3 developments; drop one or more of: inclusive jets; correlations; HF substructure; UPCs from Run 3 data; likely no effort to spare for novel techniques (e.g.ML); | cuts in the 0-2 year window ensure that the 3-5 year effort will be at "minimal" level; worth to note ALICE's Service Work obligations at 0.27FTE such that 3FTE is actual 2FTE for purely resarch tasks; some SW can be associated to upgrade projects with TDR
3-5 years: minimal | 3 | 3 | - similar - hard choice: drop physics vs. FoCal/ITS3 - no ALICE 3 R&D
6-10 years: minimal | 3 | 3 | - finalization of fraction of baseline analyses from Run 3+4; no small-x physics with FoCal; no ALICE 3 developments; likely closeout of LHC program at RNC

## ALICE3
[PROJECT] | FTE - Staff | FTE - PD | Physics program summary (highlights, deliverables, etc...) | Notes
Current FTE | 0 | 0 | ALICE 3 narrative is included on the ALICE tab
0-2 years: baseline | 0.5 | 0.5 |  | NOTE: these 2,3-5,6-10 timelines do not really fit with ALICE; ITS3/FoCal installation is 2028/9; ALICE 3 is 2035(?); expected rebalancing between projects
3-5 years: baseline | 0.5 | 1
6-10 years: baseline | 1 | 1.5 |  | More PD support would be useful
0-2 years: expanded | 1 | 1 |  | JRA: I estimated these numbers based on the ALICE/ALICE3 narrative, keeping the totals the same
3-5 years: expanded | 1.5 | 2
6-10 years: expanded | 2 | 2
0-2 years: minimal | 0 | 0 |  | [Useful to include notes on dependences, e.g. cuts in the 0-2 year window ensure that the 3-5 year effort will be at "minimal" level]
3-5 years: minimal | 0 | 0
6-10 years: minimal | 0 | 0

## JLab
[PROJECT] | FTE - Staff | FTE - PD | Physics program summary (highlights, deliverables, etc...) | Notes
Current FTE | 0.9 | 1.5
0-2 years: baseline | 0.9 | 1.5 | Active short term program in nucleon form factors, nuclei (structure/pdfs); preparation for tagged nucleon/meson structure program and Moller/SoLID (at a minimal level) | JA, ES
3-5 years: baseline | 0.8 | 1.3 | Leadership in analysis of nuclear measurements, execution of tagged-DIS measurements. Participate in early Moller running
6-10 years: baseline | 0.7 | 1 | Participation in Moller, early SoLID program; scientific leadership on PVEMC
0-2 years: expanded | 1.3 | 1.5 | Expand leadersihp in studies of nuclei (new, next-gen studies to be run in years 3-8. Expanded effort towards Moller and/or SoLID. | Probably need to know if we want a greater effort in SoLID on the ~1 year timescale (so that we are ready to define roles at that point)
3-5 years: expanded | 1.3 | 1.5 | Execute on additional physics measurements, expanded efforts towards Moller and SoLID. | Effort may be higher IF we decide to take a larger group role in SoLID (interesting physics with EIC connection, future student analysis options)
6-10 years: expanded | 1.3 | 1.5 | Greater involvement in Moller and/or SoLID. Opens up option for staff/PD/GS participation in the broader SoLID program | Effort may be higher IF we decide to take a larger group role in SoLID (interesting physics with EIC connection, student analysis options)
0-2 years: minimal | 0.8 | 1 | Complete most ongoing analyses, execute upcoming runs. Minimal-to-no role in Moller, Minimal-to-no effort to develop future physics program.
3-5 years: minimal | 0.6 | 1 | Support analyses of experiments from years 0-2; reduced tagged-DIS and/or Moller role
6-10 years: minimal | 0.5 | 0.8 | Minimal Moller and SoLID analysis.

## EIC
| FTE - Staff | FTE - PD | Physics program summary (highlights, deliverables, etc...) | Notes | FTE - Staff - breakdown | FTE - postdoc - breakdown
Current FTE | 3.9 | 1.7 | There is an additional 1.0 PD support from UCB (3.9 staff included Div. Fellow (arbitarily)
0-2 years: baseline | 6 | 6.5 | Lead role in the EIC silicon tracking/vertexing 3-4 year R&D phase + forward looking R&D towards future upgrades and/or a modest additional instrumentation role + collaboration/EIC participation (WG, TDR, LRP, etc.) |  | 4 + 0.5 + 1.5 | 4 + 0.5 + 2
3-5 years: baseline | 9.5 | 8 | Lead role in the EIC silicon tracking/vertexing ~5 year construction phase following the 3-4 year R&D + forward looking R&D towards future ugprades and/or a modest additional instrumentation role + collaboration/EIC participation | This assumes that EIC remains a high LRP priority and reasonably close to schedule. A lead role in construction will require a preceding lead role in R&D. | 8 + 0.5 + 1.5 | 6 + 0.5 + 1.5
6-10 years: baseline | 10 | 8.5 | Lead role in the EIC silicon tracking/vertexing ~5 year construction phase following the 3-4 year R&D phase | The nature of the postdoc effort will necessarily transition during this phase, as one prepares for CD-4 and start of data taking. The postdoc count will likely need to increase further to take on an additional day-1 instrumentation role. | 8 + 0.5 + 1.5 | 6 + 0.5 + 2
0-2 years: expanded | 7 | 7 | As above, with modestly expanded roles in additional R&D/instrumentation and in EIC collaboration efforts. |  | 4 + 1 + 2 | 4 + 1 + 2
3-5 years: expanded | 11 | 9 |  |  | 8 + 1 + 2 | 6 + 1 + 2
6-10 years: expanded | 11 | 10 |  | One should consider ramp-up and/or transition towards analysis efforts. | 8 + 1 + 2 | 6 + 1 + 3
0-2 years: minimal | 3.5 | 3 | Participant role in EIC silicon tracking/vertexing 3-4 year R&D phase. Give up on other (potential) instrumentation roles. Keep a minimal level of effort in the broader community/collaboration. |  | 2.5 + 0 + 1 | 3 + 0 + 0
3-5 years: minimal | 4 | 4 | Participant role in EIC silicon tracking/vertexing construction phase following the 3-4 year R&D phase. Give up on other (potential) instrumentation roles. Keep a minimal level of effort in the broader community/collaboration |  | 3 + 0 + 1 | 4 + 0 + 0
6-10 years: minimal | 4 | 5 | Participant role in EIC silicon tracking/vertexing construction phase following the 3-4 year R&D phase. Give up on other (potential) instrumentation roles. Keep a minimal level of effort in the broader community/collaboration and maintain a compromised ability to participate effectively in day-1 data taking/analysis. |  | 3 + 0 + 1 | 4 + 0 + 1

## Instrumentation
[PROJECT] | FTE - Staff | FTE - PD | Physics program summary (highlights, deliverables, etc...) | EIC FTE Staff | EIC FTE PD | ALICE FTE Staff | ALICE FTE PD | Other project staff | Other project PD | Other FTE Staff | Other FTE PD | Notes
Current FTE | 0.2 | 0 | (all counted elsewhere)
0-2 years: baseline | 5 | 5 | Complete MVTX project. LBNL takes primary leadership role for EIC silicon tracker. R&D phase lead by LBNL, influences major points to meet physics goals (eRD111, eRD113). Interface with silicon designer towards large area sensor. | 4 | 4 |  |  | 0.2 | 0.4 | 0.8 | 0.6 | ALICE ITS3 participation through EIC: test beam, sensor characterization, SD interface, wp leadership. Included in EIC numbers | How to account for non-RNC funded effort? (UCB, Si consortium,...). NA: Need to work with Barbara for UCB numbers. Numbers are for Berkeley (UCB & RNC) effort only. There will be additional effort from the EICSC. | 4.8 | 4.6
3-5 years: baseline | 6 | 7 | EIC R&D wraps up (all previous), small overlap before construction begins. Complete construction on ALICE ITS3 - LBNL participates through WPs. Construction of ALICE FOCAL & work on ALICE 3 silicon R&D. Generic R&D | 4 | 4 | 1.5 | 2.5 | 0.2 | 0.3 | 0.3 | 0.2 |  | Need to identify double counting with EIC, ALICE,... NA: numbers are now broken down by project | 5.8 | 6.7
6-10 years: baseline | 10.5 | 8.5 | LBNL leader in EIC Silicon tracker construction. Includes main construction, subsystem design/construction, technical leadership, WP leadership, topical leadership. ALICE 3 preparation and construction. Generic R&D | 8 | 6 | 2 | 2 | 0.2 | 0.3 | 0.3 | 0.2 | Quick ramp up (~6 mo - 1 year) from R&D effort to construction effort for EIC. | Verify that all numbers are FTE, not # of people. NA: They are all FTE | 10.3 | 8.2
0-2 years: expanded | 6.5 | 6.5 | More effort on generic R&D. Earlier effort on ALICE 3 and/or join ITS3 as ALICE members, rather than through EICSC | 4 | 4 | 1 | 1 | 0.3 | 0.5 | 1.2 | 1 |  | Impact of 2/5/10 year cutoffs vs natural transitions for the projects. NA: The 5 year cutoff is already a natural transition (when EIC R&D ends and construction begins). That is why there is a significant increase in FTE between 3-5 & 6-10, the ramp up is quick. | 6.2 | 6
3-5 years: expanded | 8 | 9 | More effort on generic R&D. ALICE ITS3 members. Larger effort in ALICE 3 | 4 | 4 | 3 | 4 | 0.3 | 0.4 | 0.7 | 0.6 |  |  | 7.7 | 8.6
6-10 years: expanded | 12.5 | 10.5 | Larger effort in ALICE 3 (take sizeable piece of construction). | 8 | 6 | 3.5 | 3.5 | 0.3 | 0.4 | 0.7 | 0.6 | Sizeable construction piece of ALICE 3 dependent on explanded effort in years 3-5 |  | 12.2 | 10.1
0-2 years: minimal | 3 | 3.5 | EIC silicon tracker R&D participation. No independent intellectual work. No participation in silicon design. Lose vital leadership in ensuring LBNL physics goals are met | 2.5 | 3 |  |  |  |  | 0.5 | 0.5 | Magenta numbers are staffing "beyond" what is in EIC and ALICE, and so added to totals at end. These efforts include generic R&D for developing and keeping the group's technological edge |  | 3 | 3.5
3-5 years: minimal | 3.5 | 5 | EIC R&D complete, detector design/construction lead by another institution. No effort in ALICE 3 R&D | 2.5 | 3 | 1 | 2 |  |  |  |  | Should some of the "other" be removed, e.g. if supported by LDRD, generic R&D, etc... |  | 3.5 | 5
6-10 years: minimal | 4 | 5 | EIC silicon tracker construction participation. Construction dictated by another institution. No meaningful participation in ALICE 3 | 3 | 4 | 1 | 1 | [6 empty] | 4 | 5
Note on B3: EIC leadership R&D + 1 FTE fill in (MVTX completion, interface with silicon designer, maybe some generic R&D) ======
Note on B7: EIC leadership R&D + 1 FTE fill in (MVTX completion, interface with silicon designer, maybe some generic R&D) ======

## Computing
[PROJECT] | FTE - Staff (non-project) | FTE - PD (non-project) | Physics program summary (highlights, deliverables, etc...) | Notes | TOTAL FTE - Staff | TOTAL FTE - PD
Current FTE | 0 | 0.2 | Irakli is 0.3 under ALICE, 0.7 outside (ALICE) support |  | 1 | 0
0-2 years: baseline | 0.2 | 0.5 | ALICE-USA: Continue to grow and operate Tier-2 (T2) facilities and deploy US-based ALICE Analysis Facility in addition to US T2 sites. Continue local R&D effort to exploit non-pledged resources for ALICE; Maintain Java-based ALICE middleware; Maintain support on NERSC Cori and expand to Perlmutter. STAR: Support ongoing embedding campaigns. Update workflow: Cori → Perlmutter. New tools: data transfer & authorization. Deploy data reconstruction workflow. EIC: Follow and provide feedback to ongoing EIC discussions/decisions on single software stack. | 0.5 FTE could be a PD or a PS | 1 | 0.5
3-5 years: baseline | 0.2 | 0.5 | Extend access to unique resources at NERSC. Data analysis and processing evolution into GPU/ML/AI. Support evolution of the computing systems along with LHC-HL Era tools from HEP Software foundation and new paradigms in distributed computing. Prepare for the next exascale supercomputer - NERSC-10, successor to Perlmutter. |  | 1 | 0.5
6-10 years: baseline | 0.2 | 0.5 | Rediness to support EIC and ALICE3 computing needs based on the new concepts available as a result of their computing CDRs the development concepts and tools that will stem from planning for the LHC-HL era. Plan for hosting and supporting EIC computing facility at LBNL |  | 1 | 0.5
0-2 years: expanded | 0.2 | 1 | [on top of baseline] RNC @ NERSC & LBNL-ITD: Evaluate data store on EOS/XRootD (ITD) accessibility from NERSC; Evaluate investing in the ITD CONDO model. Active involvement in EIC decisions in single software stack with particular emphasis on distributed computing model. | 1 FTE could be a PD or a PS | 1 | 1
3-5 years: expanded | 0.2 | 1 | [on top of baseline] Dedicated effort towards invlvement in AI/ML/GPU work within the group's ALICE efforts. Deeper involvement in EIC software and computing model develpment. |  | 1 | 1
6-10 years: expanded | 0.2 | 1 | [on top of baseline] Deploye EIC computing facility at LBNL as fitting with the EIC computing model |  | 1 | 1
0-2 years: minimal | 0.2 | 0 | ALICE-USA: maintain T2 facilities. Minimal maintainance of JAliEn middlware. Tansition from Cori to Perlmutter. STAR: Support ongoing embedding campaigns. Update workflow: Cori → Perlmutter. New tools: data transfer & authorization. Deploy data reconstruction workflow. EIC: support group computing needs at the NERSC cluster. | [Useful to include notes on dependences, e.g. cuts in the 0-2 year window ensure that the 3-5 year effort will be at "minimal" level] | 1 | 0
3-5 years: minimal | 0.2 | 0 | Extend access to unique resources at NERSC. Support groups needs for data analysis and processing evolution into GPU/ML/AI/new tools. Prepare for the next exascale supercomputer - NERSC-10 |  | 1 | 0
6-10 years: minimal | 0.2 | 0 | Support of group computing needs for ALICE3 and EIC experiments. |  | 1 | 0

## Template
[PROJECT] | FTE - Staff | FTE - PD | Physics program summary (highlights, deliverables, etc...) | Notes
Current FTE | 0 | 0
0-2 years: baseline | 0 | 0 | ["Baseline" corresponds to what was presented in the slides. Add a brief summary of the expected physics/outcomes assumed based on the baseline FTEs. ] | [Useful to include names *if* the effort of specific people was assumed.]
3-5 years: baseline | 0 | 0
6-10 years: baseline | 0 | 0
0-2 years: expanded | 0 | 0 | [EXPANDED program includes HIGH PRIORITY additions to the baseline program that might be important/intersting enough to shift effort here from other parts of the RNC program. Add a brief statement on the added physics/benefits.] | [Useful to include notes on dependences, e.g. 3-5 year plan is (is not) contingent on expanded effort in years 0-2]
3-5 years: expanded | 0 | 0
6-10 years: expanded | 0 | 0
0-2 years: minimal | 0 | 0 | ["Minimal" is the level below which the program may not be sufficiently interesting and/or viable to pursue. Describe losses from the baseline program if workforce set to a "minimal" level (or else explain what key parts remain)] | [Useful to include notes on dependences, e.g. cuts in the 0-2 year window ensure that the 3-5 year effort will be at "minimal" level]
3-5 years: minimal | 0 | 0
6-10 years: minimal | 0 | 0

## EIC-HF
[PROJECT] | FTE - Staff | FTE - PD | Physics program summary (highlights, deliverables, etc...) | Notes
0-2 years: baseline | 0.3 | 0.3 | conducting HF simulation studies utilizing MAPS-based tracker for HF measurements at EIC, charm F2, gluon nPDF, charm baryons, gluon DG, gluon TMDs, CNM, new observables/simulation studies | [Useful to include names *if* the effort of specific people was assumed.]
3-5 years: baseline | 0.3 | 0.5
6-10 years: baseline | 0.6 | 1 |  | Not included in totals; assumed to be part of the EIC collaboration involvements.
0-2 years: expanded | 0 | 0 | [EXPANDED program includes HIGH PRIORITY additions to the baseline program that might be important/intersting enough to shift effort here from other parts of the RNC program. Add a brief statement on the added physics/benefits.] | [Useful to include notes on dependences, e.g. 3-5 year plan is (is not) contingent on expanded effort in years 0-2]
3-5 years: expanded | 0 | 0
6-10 years: expanded | 0 | 0
0-2 years: minimal | 0 | 0 | ["Minimal" is the level below which the program may not be sufficiently interesting and/or viable to pursue. Describe losses from the baseline program if workforce set to a "minimal" level (or else explain what key parts remain)] | [Useful to include notes on dependences, e.g. cuts in the 0-2 year window ensure that the 3-5 year effort will be at "minimal" level]
3-5 years: minimal | 0 | 0
6-10 years: minimal | 0 | 0

## CE
| STAR | sPHENIX | CBM | ALICE | ALICE3 | JLab | EIC | Instrumentation | Computing | other | Outside support | Total per person
Xin | 0.5 | 0.3 |  |  |  |  | 0.2 |  |  |  |  | 1
Barbara |  |  |  | 0.3 |  |  | 0.2 |  |  |  | 0.5 | 1
Peter | 0.2 |  |  | 0.5 | [5 empty] | 0.3 |  | 1
Spencer |  |  |  | 0.5 |  |  | 0.4 |  |  | 0.1 |  | 1
Yuan |  | 0.6 |  |  |  |  | 0.2 | 0.2 |  |  |  | 1
Grazyna | 0.3 | 0.3 | [7 empty] | 0.4 |  | 1
Mateusz |  |  |  | 1 | [7 empty] | 1
Jim | 0.9 | [5 empty] | 0.1 |  |  |  |  | 1 | Jim is retiring at end of June
Nu | 0.5 | 0.2 | 0.3 | [8 empty] | 1
Nikki |  |  |  | 0.4 |  |  | 0.6 |  |  |  |  | 1
Irakli | 0.2 |  |  | 0 |  |  | 0.1 |  |  |  | 0.7 | 1 | 0.3 STAR/EIC (RNC support), 0.7 outside (ALICE) support
Ernst | [5 empty] | 0.2 | 0.8 |  |  |  |  | 1
John | [5 empty] | 0.7 | 0.3 |  |  |  |  | 1
Yue Shi | [10 empty] | 1 | 1 | Include some of this as 'expected' contribution? - No
(Div. Fellow) | [6 empty] | 1 |  |  |  |  | 1 | How this unidentified "divisional fellow" to make their promotion case in ~5 years on full time EIC effort?
| 2.6 | 1.4 | 0.3 | 2.7 | 0 | 0.9 | 3.9 | 0.2 | 0 | 0.8 | 2.2 | 15
|  |  | 4.3 |  | 2.7 | 0.9 | 1 |  |  | 12.8
Nacer |  |  |  | 1 | [7 empty] | 1
Yuanjing Ji | 0.5 | 0.3 |  |  |  |  | 0.2 |  |  |  |  | 1
Ho-San | 0.5 | 0.5 | [9 empty] | 1
Yue-Hang | 1 | [10 empty] | 1 | Yue-Hang has left RNC
Peng | [6 empty] | 1 |  |  |  |  | 1
Yu Hu | 0.5 | 0.5 | [9 empty] | 1
Guannan | 0.8 | [7 empty] | 0.2 |  |  | 1 | Guannan has left RNC
James |  |  |  | 0.5 | [6 empty] | 0.5 | 1
Raymond |  |  |  | 0.5 | [6 empty] | 0.5 | 1
Rey | [10 empty] | 1 | 1 | UCB: 50/50 ALICE and EIC
Wenqing | [10 empty] | 1 | 1 | UCB: 50/50 ALICE and EIC
Shujie | 0 |  |  |  |  | 0.7 | 0.3 |  |  |  |  | 1
Tyler | [5 empty] | 0.8 | 0.2 |  |  |  |  | 1
| 3.3 | 1.3 | 0 | 2 | 0 | 1.5 | 1.7 | 0 | 0.2 |  | 3 | 13
10

## CE - Comp
| STAR | sPHENIX | CBM | ALICE | ALICE3 | JLab | EIC | Instrumentation | Computing | other | Outside support |  | Total per person
Xin | 0.5 | 0.3 |  |  |  |  | 0.2 | [5 empty] | 1
Barbara |  |  |  | 0.3 |  |  | 0.2 |  |  |  | 0.5 |  | 1
Peter | 0.2 |  |  | 0.5 | [5 empty] | 0.3 |  |  | 1
Spencer |  |  |  | 0.5 |  |  | 0.4 |  |  | 0.1 |  |  | 1
Yuan |  | 0.6 |  |  |  |  | 0.2 | 0.2 |  |  |  |  | 1
Grazyna | 0.3 | 0.3 | [7 empty] | 0.4 |  |  | 1
Mateusz |  |  |  | 1 | [8 empty] | 1
Jim | 0.9 | [5 empty] | 0.1 | [5 empty] | 1 | Jim is retiring at end of June
Nu | 0.5 | 0.2 | 0.3 | [9 empty] | 1
Nikki |  |  |  | 0.4 |  |  | 0.6 | [5 empty] | 1
Irakli | 0.2 |  |  | 0 |  |  | 0.1 |  |  |  | 0.7 |  | 1 | 0.3 STAR/EIC (RNC support), 0.7 outside (ALICE) support
Ernst | [5 empty] | 0.2 | 0.8 | [5 empty] | 1
John | [5 empty] | 0.7 | 0.3 | [5 empty] | 1
Yue Shi | [10 empty] | 1 |  | 1 | Include some of this as 'expected' contribution? - No
(Div. Fellow) | [6 empty] | 1 | [5 empty] | 1 | How this unidentified "divisional fellow" to make their promotion case in ~5 years on full time EIC effort?
| 2.6 | 1.4 | 0.3 | 2.7 | 0 | 0.9 | 3.9 | 0.2 | 0 | 0.8 | 2.2 |  | 15
|  |  | 4.3 |  | 2.7 | 0.9 | 1 |  |  | 12.8
Nacer |  |  |  | 1 | [8 empty] | 1
Yuanjing Ji | 0.5 | 0.3 |  |  |  |  | 0.2 | [5 empty] | 1
Ho-San | 0.5 | 0.5 | [10 empty] | 1
Yue-Hang | 1 | [11 empty] | 1 | Yue-Hang has left RNC
Peng | [6 empty] | 1 | [5 empty] | 1
Yu Hu | 0.5 | 0.5 | [10 empty] | 1
Guannan | 0.8 | [7 empty] | 0.2 |  |  |  | 1 | Guannan has left RNC
James |  |  |  | 0.5 | [6 empty] | 0.5 |  | 1
Raymond |  |  |  | 0.5 | [6 empty] | 0.5 |  | 1
Rey | [10 empty] | 1 |  | 1 | UCB: 50/50 ALICE and EIC
Wenqing | [10 empty] | 1 |  | 1 | UCB: 50/50 ALICE and EIC
Shujie | 0 |  |  |  |  | 0.7 | 0.3 | [5 empty] | 1
Tyler | [5 empty] | 0.8 | 0.2 | [5 empty] | 1
| 3.3 | 1.3 | 0 | 2 | 0 | 1.5 | 1.7 | 0 | 0.2 |  | 3 |  | 13
10
Staff + Postdoc | 5.9 | 2.7 | 0.3 | 4.7 | 0 | 2.4 | 5.6 | 0.2 | 0.2 | 0.8 |  | 22.8
Reduction | 2.7 | [5 empty] | 0.1 |  | 0.2 |  |  | 3
CE Adjusted | 3.2 | 2.7 | 0.3 | 4.7 | 0 | 2.4 | 5.5 | 0.2 | 0 | 0.8 |  | 19.8
Planning in plot | 4.4 | 2.5 | 0.3 | 5 | 1 | 2.6 | 8.2 | 0 | 0 | 0 |  | 24
Difference | -1.2 | 0.2 | 0 | -0.3 | -1 | -0.2 | -2.7 | 0.2 | 0 | 0.8 | 0 | -4.2

## Totals
[PROJECT] | FTE - Staff | FTE - PD | Physics program summary (highlights, deliverables, etc...) |  | Notes | Baseline w/o CBM, ALICE3 (-1, -2 w/o FoCal) |  | STAR | sPHENIX | CBM | ALICE | ALICE3 | JLab | EIC | Instrumentation | Computing
Current FTE | 12 | 9.7 | 0.8 staff FTE currently listed as "other" (admin or other physics) --> 12.8 total |  |  |  |  | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 0
0-2 years: baseline | 14.5 | 17.6 | ["Baseline" corresponds to what was presented in the slides. Add a brief summary of the expected physics/outcomes assumed based on the baseline FTEs. ] |  | For instrumentation, I am using columns K&L ("other" FTE) to avoid double counting ALICE and EIC effort | 13.7 | 17.1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
3-5 years: baseline | 17.2 | 18.25 |  |  | Assuming that 0.8+0.0 FTE staff from computing are included in various projects | 16.1 | 16.75 | 15.1 | 14.75 | BASELINE FTEs WITHOUT CBM AND ALICE3
6-10 years: baseline | 17.2 | 17.45 |  |  | Not including FTEs from "EIC-HF" - these are considered as contributing to the EIC collaboration/participation numbers | 15.3 | 14.95
0-2 years: expanded | 18.75 | 23 | [EXPANDED program includes HIGH PRIORITY additions to the baseline program that might be important/intersting enough to shift effort here from other parts of the RNC program. Add a brief statement on the added physics/benefits.]
3-5 years: expanded | 23.8 | 25.1 |  |  |  | 15.9 | 15
6-10 years: expanded | 22.2 | 24.9 |  |  |  | 3.7 | 4.75
0-2 years: minimal | 8 | 7.5 | ["Minimal" is the level below which the program may not be sufficiently interesting and/or viable to pursue. Describe losses from the baseline program if workforce set to a "minimal" level (or else explain what key parts remain)]
3-5 years: minimal | 7.8 | 8
6-10 years: minimal | 7.7 | 8.8
|  |  | JRA: these notes are out of date | Non-RNC guess? | Status
CURRENT EFFORT | 12.8 | 10 | 0-2 year baseline is 1.8 + 7.8 FTE over | 0 + 2 | Doable if we can trim few PDs?
|  |  | 3-5 year baseline is 5.2 + 8.5 FTE over | ? | Have to assume that SOME but not all new projects go forward, still need to trim
|  |  | 6-10 year baseline is 5.3 + 8.7 FTE over | ? | Have to assume that SOME but not all new projects go forward, still need to trim